## CTVP Pack
FILIET: An Information Extraction System for Disaster-Related Tweets
Central Testing and Validation Procedure Pack
Pack A: CRAWLER MODULE TEST SCRIPTS/PLANS
Test Script Number | Test Description | Test Input | Test Expected Output | Test Acceptance Criteria | Test Steps | Test Status
CR-001 | Check if the crawler collects tweets given the specified hashtags | List of hashtags | Prints the tweet | The new tweets contained at least one of the specified hashtags | 1. The user will provide the tweets
2. The system will listen for incoming tweets
3. The system will store the database
CR-002 | Check if the tweets contained special characters/encoding | [tweet] | Prints ("This tweet cannot be stored") | The system does not store the tweets | 1. The user will provide the tweets
|  | Please refer to (http://emojipedia.org/twitter-emoji-list/) for the list of emojis |  |  | 2. The system will listen for incoming tweets
3. The system will store the database
CR-003 | Check if the crawler can connect to Twitter | AccessKey=2713608146-GJ2b02dsnctbDAeenRlG67VJy1d6fyyE17GcOCs | The crawler is now streaming. | The system is now printing the tweets coming from the user's account. | 1. Change the access key, access secret, consumer key and consumer secrets in the resources > twitter.properties
AccessSecret=3RnODV1MVw3ESgifpbgZkEQxT25v2bKA02grgl0cMkFXp
|  | ConsumerKey=QWkcbXqh3ojP80YEdS1PpgUaR |  |  | 2. Run the system
ConsumerSecret=OtkCridwMEqK1hh7qsN2bknt010wyIU2wRLPLLUS7KVWHselsa
CR-004 | Check if the crawler can not connect to Twitter | AccessKey=2713608146-GJ2b02dsnctbfdsfdsfh4353 | The crawler cannot connect to Twitter. | The system will display connection error messages (API stacktrace) | 1. Change the access key, access secret, consumer key and consumer secrets in the resources > twitter.properties
AccessSecret=3RnODV1MVw3ESgifpbgZkEQxT25v2bKA02grgl0cMkFXp
|  | ConsumerKey=QWkcbXqh3ojP80YEdS1PpgUaR |  |  | 2. Run the system
ConsumerSecret=OtkCridwMEqK1hh7qsN2bknt010wyIU2wRLPLLUS7KVWHselsa
Pack B: FEATURE EXTRACTION MODULE TEST SCRIPTS/PLANS
Test Script Number | Test Description | Test Input | Test Expected Output | Test Acceptance Criteria | Test Steps | Test Status
FE-001 | Check if the training data can be loaded into the system correctly | Cleaned-Categorized-JP-3.csv | Prints the values of each columns (Prints each value in a separate line) | The training data is now loaded into the system | 1. The user provides the path to the training data.
|  | char-ngram [file] |  |  | 2. Run the system
wordcounts [file]
attributes[file]
FE-002 | Check if the features are extracted from a CSV file | Cleaned-Categorized-JP-3.csv | CSV file is containing the extracted features (Please refer to char-ngram and wordcount for the list of features[ resources > models > charngram, resources > models > word) | The values of the extracted features must be correct. (Refer to Thesis document for the values of each attributes) | 1. The user provides the path to the training data.
|  | char-ngram [file] |  |  | 2. Run the system
wordcounts [file]
attributes [file]
FE-003 | Check if the features are extracted from a single input | [tweet] | Prints the values of the features (Please refer to char-ngram and wordcount for the list of features[ resources > models > charngram, resources > models > word) | The values of the extracted features must be correct. (Refer to Thesis document for the values of each attributes) | 1. The user will provide a tweet.
|  | char-ngram [file] |  |  | 2. Run the system
wordcounts [file]
attribute [file]
Pack C: CLASSIFIER MODULE TEST SCRIPTS/PLANS
Test Script Number | Test Description | Test Input | Test Expected Output | Test Acceptance Criteria | Test Steps | Test Status
CL-001 | Check if model can be read | Model file (kNN-7.model) | Prints ("Load successful") | It does not produce error messages | 1. The user provides the path to the model
2. Run the system
CL-002 | Check if the correct class label was specified | Model file (kNN-7.model) | Prints ("Category") | "Category" was printed | 1. Run the system
CL-003 | Check if the model file exists | not-an-existing.model | Prints ("No model found") | The system displays an error message. | 1. The user provides the path to the training data.
2. The system loads the data.
CL-004 | Check if the classifier categorized the tweet correctly | [Caution & Advice tweets] | Prints("Category: CA") | The classifier and the user's classification must be the same. | 1. The user provides the path to the model file
2. The user provides the tweet to be classified
|  | kNN-7.model |  |  | 3. Run the system
CL-005 | Check if the classifier categorized the tweet correctly | [Casualties & Damage tweets] | Prints("Category: CD") | The classifier and the user's classification must be the same. | 1. The user provides the path to the model file
2. The user provides the tweet to be classified
|  | kNN-7.model |  |  | 3. Run the system
CL-006 | Check if the classifier categorized the tweet correctly | [Donation tweets] | Prints("Category: D") | The classifier and the user's classification must be the same. | 1. The user provides the path to the model file
2. The user provides the tweet to be classified
|  | kNN-7.model |  |  | 3. Run the system
CL-007 | Check if the classifier categorized the tweet correctly | [Others tweets] | Prints("Category: O") | The classifier and the user's classification must be the same. | 1. The user provides the path to the model file
2. The user provides the tweet to be classified
|  | kNN-7.model |  |  | 3. The system reads the model file.

## Objectives and Heuristics
Test Objectives | Test Heuristics
To test if the crawler collects the needed tweets | Follow the data
To test if the feature extractor is able to correctly extract the features
To test if the classifier is able to classify the tweets into its correct category
To improve the accuracy of the modules

## Sheet7 (hidden)
Test Case | Description | Input | Output | Preconditions | Steps | Postconditions | Acceptance Criteria | Result | Test Objectives
CR-001 | Check if the crawler collects tweets given the specified hashtags | List of hashtags | Prints the tweet | The system must be connected to the internet and Twitter. | 1. The user will provide the tweets | The system stores the tweets in the database. | The tweets contained at least one of the specified hashtags |  | To test if the crawler collects the needed tweets
2. The system will listen for incoming tweets
3. The system will store the database
CR-002 | Check if the tweets contained special characters/encoding | [tweet] | This tweet cannot be stored | The system must be connected to the internet and Twitter. | 1. The user will provide the tweets |  | The system does not store the tweets
2. The system will listen for incoming tweets
3. The system will store the database
CR-003 | Check if the crawler can connect to Twitter | Access Key | The crawler is now streaming. | The system must be connected to the internet. | 1. The user provides the tokens and secrets |  | The system is streaming the user's timeline.
|  | Access Secrets |  |  | 2. The system will connect to Twitter via Twitter API
Consumer Key
Consumer Secret
CR-004 | Check if the crawler can connect to Twitter | Invalid Access Key | The crawler cannot connect to Twitter. | The system must be connected to the internet. | 1. The user provides the tokens and secrets |  | The system is not streaming the user's timeline.
|  | Access Secrets |  |  | 2. The system will connect to Twitter via Twitter API
Consumer Key
Consumer Secret
CR-005 | Check if the crawler can connect to Twitter | Access Key | The crawler cannot connect to Twitter. | The system must be connected to the internet. | 1. The user provides the tokens and secrets |  | The system is not streaming the user's timeline.
|  | Invalid Access Secrets |  |  | 2. The system will connect to Twitter via Twitter API
Consumer Key
Consumer Secret
CR-006 | Check if the crawler can connect to Twitter | Access Key | The crawler cannot connect to Twitter. | The system must be connected to the internet. | 1. The user provides the tokens and secrets |  | The system is not streaming the user's timeline.
|  | Access Secrets |  |  | 2. The system will connect to Twitter via Twitter API
Invalid Consumer Key
Consumer Secret
CR-007 | Check if the crawler can connect to Twitter | Access Key | The crawler cannot connect to Twitter. | The system must be connected to the internet. | 1. The user provides the tokens and secrets |  | The system is not streaming the user's timeline.
|  | Access Secrets |  |  | 2. The system will connect to Twitter via Twitter API
Consumer Key
Invalid Consumer Secret
FE-001 | Check if the training data can be loaded into the system correctly | Cleaned-Categorized-JP-3.csv | Prints the values of each columns | Delimiters for the training data must be ';' | 1. The user provides the path to the training data. |  | The training data is now loaded into the system |  | To test if the feature extractor is able to correctly extract the features
|  | char-ngram [file] |  | Each input the CSV file must only be 1 line.
wordcounts [file]
FE-002 | Check if the features are extracted from a CSV file | Cleaned-Categorized-JP-3.csv | CSV file containing the extracted features | Delimiters for the training data must be ';' | 1. The user provides the path to the training data. |  | The values of the extracted features must be correct.
|  | char-ngram [file] |  |  | 2. The system loads the model files (char-ngram and wordcounts)
|  | wordcounts [file] |  |  | 3. The system extracts the word features.
4. The system extracts the n-gram features.
FE-003 | Check if the features are extracted from a single input | [tweet] | Prints the values of the features | The system must passed through the preprocessing module. | 1. The system loads the model files (char-ngram and wordcounts). |  | The values of the extracted features must be correct.
|  | char-ngram [file] |  |  | 2. The system extracts the word features.
|  | wordcounts [file] |  |  | 3. The system extracts the n-gram features.
FE-004 | Check if the features are extracted from a single input | [tweet] | Prints the values of the word features | The system must passed through the preprocessing module. | 1. The system loads the model files (char-ngram and wordcounts). |  | The values of the extracted features must only be the word features.
|  | Invalid char-ngram [file] |  |  | 2. The system extracts the word features.
|  | wordcounts [file] |  |  | 3. The system extracts the n-gram features.
FE-005 | Check if the features are extracted from a single input | [tweet] | Prints the values of the n-gram features | The system must passed through the preprocessing module. | 1. The system loads the model files (char-ngram and wordcounts). |  | The values of the extracted features must only be the n-gram features.
|  | char-ngram [file] |  |  | 2. The system extracts the word features.
|  | Invalid wordcounts [file] |  |  | 3. The system extracts the n-gram features.
FE-006 | Check if the training data file exists | [non-existent file] | The file does not exist |  | 1. The user provides the path to the training data. |  | The system displays an error message.
2. The system loads the data.
FE-007 | Check if the training data file exists | Cleaned-Categorized-JP-3.csv | Load successful |  | 1. The user provides the path to the training data. |  | The system has successfully loaded the CSV file.
2. The system loads the data.
CW-001 | Check if model can be read | Model file (kNN-7.model) | Load successful | Model file must come from Weka (GUI) | 1. The user provides the path to the model |  | It does not produces error messages |  | To test if the classifier is able to classify the tweets into its correct category
2. The system loads the model file
CW-002 | Check if the correct class label was specified | Model file (kNN-7.model) | Prints "Category" | Model file must come from Weka (GUI) | 1. The user provides the path to the model |  | "Category" was printed
2. The system loads the model file
CW-003 | Check if the model file exists | [non-existent file] | The file does not exist |  | 1. The user provides the path to the training data. |  | The system displays an error message.
2. The system loads the data.
CW-003 | Check if the classifier categorized the tweet correctly | [tweet] | Category: CA |  | 1. The user provides the path to the model file |  | The classifier and the user's classification must be the same.
|  | kNN-7.model |  |  | 2. The user provides the tweet to be classified
3. The system reads the model file.
4. The system classify the tweet